## CARIBE-EWS ACTION MONITOR
ACTION CODE | ACTION DESCRIPTION | REFERENCE | LEAD | DEADLINE | COMPLETION | STATUS | COMMENTS | REVIEW NOTES
C-2023-04-00 | Identify the venue and dates of ICG/CARIBE EWS-XVII | ICG/CARIBE EWS-XVI | TS, Chair | 2023-12 | 2024-04 | COMPLETED | ICG/CARIBE-EWS took place during 6-9 May 2024 in Müanagua-Nicaragua.
C-2023-04-01 | CATAC to act as a regional real-time seismic data aggregator/hub for Central America | ICG/CARIBE EWS-XVI | CATAC | 2024-12 |  | IN PROGRESS | CATAC is expected to report to the SC in its 2025/01 meeting.
C-2023-04-02 | Conduct a study to demonstrate improvement in tsunami early warning times with two to four variations on SMART Cable designs | ICG/CARIBE EWS-XVI | WG2 | 2024-12 |  | IN PROGRESS | WG2 reported to the SC in its 2025/01 meeting.
C-2023-04-03 | Engage industry to understand which telecommunications cables are scheduled for replacement or new installations | ICG/CARIBE EWS-XVI | WG2, TS | 2024-06 |  | IN PROGRESS | WG2 reported to the SC in its 2025/01 meeting. Please also see C-2024-02-18.
C-2023-04-04 | Initiate contacts with the identified volcano observatories and/or institutes responsible for monitoring volcanoes threatening the CARIBE-EWS, to implement the MoU with the VONUT | ICG/CARIBE EWS-XVI | WG2, TS | 2024-06 |  | IN PROGRESS | An effort is in place to issue a CL to inform Member States on the report on Monitoring and warning for tsunamis generated by volcanoes (IOC/2024/TS/183) and call for global/regional webinars to promote synergies between Volcano Observatories/VAACs. CARIBEWAVE26 is expected to include a TGV scenario. | One of the scenarios for CW26 is to be Volcano Generated Tsunami
C-2023-04-05 | List of volcanoes and volcano observatories and the VONUT to be shared with the Ad Hoc Team on TGV of TOWS-WG-TT-TWO | ICG/CARIBE EWS-XVI | WG1,WG2 | 2024-02 | 2024-02 | COMPLETED
C-2023-04-06 | Organize an Experts Meeting on “Non-Seismic Sources of Tsunamis for the Caribbean and Adjacent Regions" | ICG/CARIBE EWS-XVI | WG1, TS | 2024-12 | 2024-12 | IN PROGRESS | Organized in Hedia-Costa Rica during 3-5 December 2024. The report is expected to be published in 2025/Q3. | Missing report
C-2023-04-07 | Execute a regional training on the development of Digital Elevation Models for tsunami inundation modelling | ICG/CARIBE EWS-XVI | WG1, TS | 2024-12 |  | IN PROGRESS | Please refer to C-2024-02-17
C-2023-04-08 | Organize and conduct a Meeting of Experts for Seismic Sources in the Northwest Caribbean | ICG/CARIBE EWS-XVI | WG1, TS | 2024-12 |  | IN PROGRESS | Organized in Hedia-Costa Rica during 3-5 December 2024. The report is expected to be published in 2025/Q3.
C-2023-04-09 | Determine the target number of communities in the CARIBE-EWS for Tsunami Ready recognition by 2030 | ICG/CARIBE EWS-XVI | CTIC,WG4,TS | 2024-12 |  | IN PROGRESS | M. Peroche presented the methodology to the ODTP-SC-5 during 16-17 January 2025 and TOWS-WG-XVIII during 24-25 February 2025 and received suggestions for updates.
C-2023-04-10 | Finalize the translation of Manual and Guides 86 into Spanish | ICG/CARIBE EWS-XVI | TS, Chair | 2024-02 | 2024-02 | COMPLETED
C-2023-04-11 | Coordinate the posting and distribution of the current version of the CARIBE-EWS Tsunami Signage Inventory and Report and provide an updated version for the next ICG session | ICG/CARIBE EWS-XVI | ITIC-CAR,CTIC,TS | 2024-05 | 2024-05 | IN PROGRESS
C-2023-04-12 | CARIBE WAVE 24 will take place on Thursday, 21 March 2024, commencing at 15:00 UTC | ICG/CARIBE EWS-XVI | TT-CW | 2024-03 | 2024-03 | COMPLETED
C-2023-04-13 | Final admission of CATAC as TSP in June 2024 | ICG/CARIBE EWS-XVI | ICG/CARIBE EWS | 2025-05 |  | IN PROGRESS | Decision will be taken at the ICG/CARIBE-EWS XVIII taking into consideration of the updated versions of i) the CATAC User's Manual, ii) GSDD and iii) Technical, Logistical and Administrative Requirements of a Regional Tsunami Service Provider for CARIBE-EWS.
C-2023-04-14 | The ICG also recommended TOWS-WG to identify a mechanism to cross credit other Members States assessment, preparedness, and response efforts with the UNESCO-IOC TRRP. | ICG/CARIBE EWS-XVI | TOWS-WG | 2024-12 |  | IN PROGRESS | TOWS-WG-XVIII appreciated the progress made for establishing the Tsunami Ready Equivalency for the PTWS by developing a draft guidance using the Tsunami Ready indicators as a foundation. ICG/PTWS XXXI approved the provisional PTWS Tsunami Ready Equivalency Guidance for piloting.
C-2023-04-15 | CATAC will update its Users Guide, taking into account the new processing methods, messaging formats and channels | ICG/CARIBE EWS-XVI | CATAC | 2025-04 | 2024-04 | COMPLETED | Dr. Wilfried Strauch informed WG3 that the updated Users Guide shold be available by Dec. 31, 2024 (October 8, 2024). This timeline was updated as end of February 2025 at the WG3 Meeting on 24 January. The revised version was made available to the ICG/PTWS XXXI (7-11 April 2025, Beijing, China). Shared with the WG3 on 23 April 2025.
C-2023-04-16 | CATAC will present the updated User ́s Guide to WG-CA and ICG/PTWS XXXI in Sep 2023 for consideration for implementation for the Pacific coast of Central America. | ICG/CARIBE EWS-XVI | CATAC | 2025-04 |  | IN PROGRESS | Please also see C-2023-04-15
C-2023-04-17 | CATAC will present the updated users guide at the ICG/CARIBE-EWS-XVII. | ICG/CARIBE EWS-XVI | CATAC | 2024/05 |  | FAILED
C-2023-04-18 | WG3 to review and revise Technical, Logistical and Administrative Requirements of a Regional Tsunami Service Provider for CARIBE EWS and report to the ICG/CARIBE-EWS-XVII | ICG/CARIBE EWS-XVI | WG3, Steering Committee | 2025/05 |  | IN PROGRESS | The SC of ICG CARIBE-EWS took on the review of the document in light of the GSDD. The Chair of WG3 provided input to the SC on behalf of WG3.
C-2024-02-01 | Revamp CTIC Board Meetings | MTOM 2024/02 | CTIC, TS | 2024-06 |  | NOT STARTED
C-2024-02-02 | Develop a Global TR Progress Monitoring Tool to provide an overview on the implementation of all TR type programs | MTOM 2024/02 | TS,WG4 | 2024-12 |  | IN PROGRESS | A Draft version has been developed and is being used internally by the IOC/TSR.
C-2024-02-03: | Advance planning for a CTIC/ITIC-CAR Multi-Annual Community Tsunami Exercise training in the fringes of the next ICG session with funding from the USAID/BHA is ongoing. | MTOM 2024/02 | CTIC,ITIC-CAR,TS | 2024-05 | 2024-08 | COMPLETED | Please also see C-2024-05-14.
C-2024-02-04 | Haiti will communicate National Office of Civil Aviation (OFNAC) as a TWFP-Alternate | MTOM 2024/02 | Chair | 2024-05 |  | IN PROGRESS | No such communication toom place yet. G. Metayer is expected to report to the SC in its 2025/01 meeting.
C-2024-02-05 | PTWC distribute the updated Users’ Guide which will also incorporate information from the 2006 Communication Plan for review, comments, and approval prior to next ICG-CARIBE-EWS Session (PTWC). | MTOM 2024/02 | PTWC, TS | 2024-05 |  | IN PROGRESS | Dr. Charles McCreery shared the updated Users Guide with WG3 on October 8, 2024. The document was reviewed by the WG3. PTWC was suggested to make some changes. To be presented at ICG/CARIBE-EWS XVIII.
C-2024-02-06 | Organize a training course to be taught in English on the general principles of installation and maintenance of sea level stations and the use of tide gauge data | MTOM 2024/02 | WG2, TS | 2024-12 |  | IN PROGRESS | Letters were sent to PRSN and CARICOOS and and agreements were received on their co-hosting for this course in Puerto Rico (San Juan or Mayagüez) during (tentatively) 7-11 July 2025. A revised assessment indicated the need to shift this training to 2025/11 to be conducted in a different Member State.
C-2024-02-07 | Clarifications will be requested at the TOWS-WG-XVII meeting on the KPI reporting with respect to ODTP | MTOM 2024/02 | TOWS-WG Rep, TS | 2024-02 |  | IN PROGRESS | Progress has been presented during the ODTP-SC-5 (16-17 January 2025)
C-2024-02-08 | Review of Tsunami Watch Operation Global Service Document (IOC Technical Series 130) for the submission of comments by ICG CARIBE EWS by 2024. | MTOM 2024/02 | TOWS-WG Reps, Chair | 2024-05 | 2024-05 | COMPLETED | WG3 received a copy of the GSDD on October 8, 2024. Plan is to review and submit comments by January 15. The final draft version of the GSDD was presented to the ICG/PTWS XXXI (7-11 April 2025, Beijing, China). ICG/CARIBE-EWS SC became the lead and WG3 Chair submitted WG3 comments to the ICG/CARIBE-EWS SC.
C-2024-02-09 | Propose ICG/CARIBE EWS-XVII to establish a stand-alone Tsunami Ready Task Team | ICG/CARIBE EWS-XVI | WG4,Chair | 2024-05 | 2024-05 | COMPLETED
C-2024-02-10 | CARIBE WAVE 2024 Participant Handbook should be updated latest early March once corrected CATAC messages are available | MTOM 2024/02 | CATAC | 2024-03 |  | FAILED
C-2024-02-11 | Strengthening Cooperation Between IOCARIBE and ICG/CARIBE EWS to be included in the agenda of the ICG/CARIBE EWS-XVII | MTOM 2024/02 | Chair, TS | 2024-05 | 2024-05 | COMPLETED
C-2024-02-12 | Inquire Dominican Republic’s availability to host the ICG/CARIBE EWS-XVII | MTOM 2024/02 | TS, Chair | 2024-02 | 2024-02 | COMPLETED
C-2024-02-13 | Marie-Noëlle Raveau to provide information on Martinique's availability to host ICG/CARIBE EWS-XVII by 16 February 2024 | MTOM 2024/02 | Marie-Noëlle Raveau | 2024-02 | 2024-02 | COMPLETED
C-2024-02-14 | Wilfried Strauch to provide information on Nicaragua's availability to host ICG/CARIBE EWS-XVII | MTOM 2024/02 | Wilfried Strauch | 2024-02 | 2024-02 | COMPLETED
C-2024-02-15 | Identify the venue and dates of the Expert Meetings on Non-Seismic Sources of Tsunamis for the Caribbean | MTOM 2024/02 | WG1, TS | 2024-03 | 2024-03 | COMPLETED | Organized in Hedia-Costa Rica during 3-5 December 2024
C-2024-02-16 | Identify the venue and dates of the Expert Meetings on Seismic Sources in the Northwest Caribbean | MTOM 2024/02 | WG1, TS | 2024-03 | 2024-03 | COMPLETED | Organized in Hedia-Costa Rica during 3-5 December 2024
C-2024-02-17 | Identify the venue and dates of the regional training on the development of Digital Elevation Models for tsunami inundation modelling | MTOM 2024/02 | WG1, TS | 2024-03 |  | IN PROGRESS
C-2024-02-18 | Organize a SMART Cable webinar targeting the Caribbean Region | MTOM 2024/02 | WG2, TS | 2024-06 |  | IN PROGRESS | Chair of WG-2 is in contact with the representatives of the SMART Subsea Cables JTF.
C-2024-05-01 | Establish Tsunami Ready Task Team | ICG/CARIBE-EWS XVII | WG2 | 2024-12 | 2024-05 | COMPLETED
C-2024-05-02 | Formation of a sub-group under Working Group 2 to specifically address the implementation of such technology in the CARIBE-EWS. | ICG/CARIBE-EWS XVII | WG2 | 2024-12 |  | IN PROGRESS | WG-2 will update the SC during its meeting in 2025/01.
C-2024-05-03 | Revamp the initiative for Group of Experts (GoE) on work and implementation plan to enhance the warning system by including other coastal hazards and adopted Recommendation ICG/CARIBE-EWS-XII.7. | ICG/CARIBE-EWS XVII | SC, TS | 2024-12 |  | IN PROGRESS | IOCARIBE IGM XVII and Technical Science Meeting (A Warming Ocean) will take place during 31 March - 04 April 2025, which may provide a good opportunity to revamp this GoE. This issue will be addressed by Dr. Silvia Chacon Barrantes at the IOCARIBE-XVIII (22-25 April 2025).
C-2024-05-04 | Identification of ICG/CARIBE-EWS XVIII (2025) Host Country | ICG/CARIBE-EWS XVII | MS, TS | 2024-09 |  | FAILED | As no confirmations were received from France (Martinique) and Panama, the ICG/CSARIBE-EWS XVIII will be held online. While the proposed time window was the week of 6 May, the SC made a decision to hold this session online.
C-2024-05-05 | Investigate the possibility for Barbados to host ICG/CARIBE-EWS XIX (2026) | ICG/CARIBE-EWS XVII | Barbados, Chair, TS | 2025-08 |  | IN PROGRESS | A letter was sent to CZMU on 14 October 2024 and several meetings were held. CTIC is assiting the CZMU in drafting a Cabinet Ppaer to ensure necessary budgetary allocations.
C-2024-05-06 | Organize an event back-to-back with ICG/CARIBE-EWS XIX in close coordination with IOCARIBE, WMO, UNDRR and other stakeholders to promote accomplishments of the ICG/CARIBE-EWS. | ICG/CARIBE-EWS XVII | SC, Barbados, TS | 2025-08 |  | NOT STARTED
C-2024-05-07 | Organize sea level training courses in English and Spanish languages in alternating years with the support of NOAA and the Secretariat, and in close collaboration with the International Hydrographic Organization (IHO) and the International Maritime Organization (IMO). | ICG/CARIBE-EWS XVII | WG2, NOAA, IHO, IMO, TS | 2024-12 |  | IN PROGRESS | A training for a SL is planned in July 2025. Please see C-2024-02-06.
C-2024-05-08 | Review and revise Technical, Logistical and Administrative Requirements of a Regional Tsunami Service Provider for CARIBE-EWS and present at its XVIII session at the latest | ICG/CARIBE-EWS XVII | WG3, Steering Committee | 2025-05 |  | IN PROGRESS | Working Group 3 met on October 8 and a sub group has been established to review and submit feedback by January 14. Action is to be transferred to the SC to be finalized by the end 2025/03 at the latest. WG 3 provided comments to SC. WG3 will provide an update at the ICG/CARIBE-EWS XVIII.
C-2024-05-09 | Explore and inform at ICG/CARIBE-EWS XVIII the integration of EEW applications for disseminating its tsunami services and products to its TWFP and NTWCs. | ICG/CARIBE-EWS XVII | CATAC | 2025-05 |  | IN PROGRESS | Wilfried Strauch of CATAC informed that there will be a Central America meeting on Nov. 18-22 and will discuss. Further updates will be presented at the ICG/CARIBE-EWS XVIII.
C-2024-05-10 | Develop a strategic plan to mobilize funding and in-kind support for more effective Tsunami Warning and Dissemination with a particular focus for LDCs and SIDS. | ICG/CARIBE-EWS XVII | SC, TS | 2025-05 |  | NOT STARTED | This is a collective task for the SC and it would be advisable to organize a meeting dedicated on this issue.
C-2024-05-11 | PRSN to host a workshop on Evacuation Mapping. | ICG/CARIBE-EWS XVII | PRSN, WG4, TS | 2024-12 |  | NOT STARTED
C-2024-05-12 | ITIC-CAR to provide an intern for 10 weeks to support the implementation of the Tsunami Ready survey in the ICG/CARIBE-EWS | ICG/CARIBE-EWS XVII | ITIC-CAR,CTIC,TS | 2024-08 | 2024-08 | COMPLETED
C-2024-05-13 | Evaluate the implementation process of the Tsunami Ready Evaluation Form in ICG/CARIBE-EWS and informs the ICG/CARIBE-EWS in the implementation of this effort in other ICGs in accordance with the TOWS-WG-XVII recommendation | ICG/CARIBE-EWS XVII | SC, TS, TT-TTR, WG4 | 2025-05 |  | IN PROGRESS | This will be considered during the upcoming TOWS-WG Meetings in 2025/02. TOWS-WG Representatives of the ICG/CARIBE-EWS will inform the ICG/CARIBE-EWS XVIII.
C-2024-05-14 | Organize a joint training on Manuals and Guides 86 and CARIBE WAVE Task Team meeting in Antigua and Barbuda | ICG/CARIBE-EWS XVII | CTIC, ITIC-CAR, WG4, TT-CW | 2025-05 |  | IN PROGRESS | Planning is in progress to conduct the training during 2025/Q4, but there is a strong likelihood that this training may take place earliest in 2026.
C-2024-05-15 | Facilitate the testing and use of the OTGA Tsunami Awareness and Tsunami Ready courses | ICG/CARIBE-EWS XVII | WG4, CTIC | 2025-05 |  | COMPLETED | Courses are available in OTGA and e-mails were sent to ICG/CARIBE Member States to facilitate their use.
C-2024-05-16 | Conduct CARIBE WAVE 25 | ICG/CARIBE-EWS XVII | TT-CW, TS | 2025-03-20 |  | COMPLETED | CL-3018 has been issued on 13 December 2024. Webinars are being organized on 21/22/23 January and 25/26/27 February in EN/ES/FR. Draft Report of the Exercise will be presented to the ICG/CARIBE-EWS XVIII.
C-2024-05-17 | Review and consider updates to the CARIBE WAVE Post-Exercise Questionnaire. | ICG/CARIBE-EWS XVII | TT-CW | 2024-12 | 2024-12 | COMPLETED | Only one reccomendation was received for CW25.
C-2024-05-18 | Explore opportunities to further involve national and regional maritime and port authorities in the CARIBE WAVE 25 so they may exercise their plans and procedures. | ICG/CARIBE-EWS XVII | TT-CW | 2024-12 |  | NOT STARTED | TT CARIBE WAVE will report to the ICG/CARIBE-EWS XVIII.
C-2024-05-19 | Share as soon as available the updated GSDD with CATAC, PTWC and Working Groups 3 and 4. | ICG/CARIBE-EWS XVII | TS, CATAC, PTWC, WG3, WG4 | 2024-09 |  | IN PROGRESS | WG3 received a copy of the GSDD on October 8, 2024. Plan is to review and submit comments by January 15. No updates were received as of 22 January. The final draft version of the GSDD was presented to the ICG/PTWS XXXI (7-11 April 2025, Beijing, China). See also C-2024-02-08.
C-2024-05-20 | Strategic review of the staffing resources needed to ensure adequate capacity at the CTIC to effectively execute and implement the programmatic and project activities to support the ICG/CARIBE EWS and EW4All frameworks | ICG/CARIBE-EWS XVII | SC, CTIC, TS | 2025-05 |  | NOT STARTED | This is a collective task for the SC and it would be advisable to organize a meeting dedicated on this issue. See also C-2024-02-01.
C-2024-05-21 | Strategic review by the CARIBE EWS Steering Committee of the CTIC Governance structure in identifying and supporting the implementation of resource mobilization, staff, partnerships, and other frameworks to enhance the ownership and sustainability of the CTIC. | ICG/CARIBE-EWS XVII | SC | 2025-05 |  | NOT STARTED | This is a collective task for the SC and it would be advisable to organize a meeting dedicated on this issue. See also C-2024-02-01.
C-2024-05-22 | Use the Inventory and EW4ALL initiatives to document the dissemination capabilities, existing alert guidance and capacity enhancement needs in each of the Member States of the ICG/CARIBE-EWS, especially best practices, including traditional and technological solutions to expand methods and systems for the reception of products from the TSPs and dissemination of warnings, define warning authorities and competencies, and address local tsunamis. | ICG/CARIBE-EWS XVII | WG3 | 2025-05 |  | COMPLETED | WG3 will be presenting results of survey to ICG/CARIBE-EWS XVIII.
C-2024-05-23 | Consider organizing the 2nd Tsunami Ready Summit back-to-back to the ICG/CARIBE-EWS XVIII to review the benefits and lessons learned and establish a road map towards 100% communities prepared for and resilient to tsunamis through efforts like Tsunami Ready | ICG/CARIBE-EWS XVII | WG4, CTIC,TT-TR, TS | 2025-05 |  | IN PROGRESS | Panama has been identified as a potential Host Country to host. Target dates: 2-4 December or 9-11 December 2025. Main Focus: Identifying sustainable pathways to reach the 2nd Objective of the ODTP. Recent developments indicate that this Summit cannot take place before 2026.
C-2024-05-24 | Publish CARIBE WAVE 24 Report | ICG/CARIBE-EWS XVII | TT-CW, ITIC-CAR, TS | 2024-12 | 2025-01 | COMPLETED | The report has been published on 2025/01.
C-2024-05-25 | Publish ICG/CARIBE-EWS XVII Executive Summary | ICG/CARIBE-EWS XVII | TS | 2024-05 |  | COMPLETED | The Executive Summary of the ICG/CARIBE-EWS XVII was made available to the Member States prior to the EC-57 in 2024/06.
C-2024-05-26 | Publish ICG/CARIBE-EWS XVII Summary Report | ICG/CARIBE-EWS XVII | TS | 2024-12 |  | DELAYED | The draft report has been delivered to the IOC Publication Officer on 24 March 2025 and awating publication.
C-2024-06-01 | Actively engage with Argentina regarding Argentinian Search and Rescue (SAR) and NAVAREA VI coordination responsibilities. | EC-57 | Chair, TS | 2025-05 |  | IN PROGRESS | Argentina has been invited to ICG/CARIBE-EWS XVIII and nomination for the delegate has been received. Please refer to ICG/PTWS XXXI Recommendations for further guidance.
ICG/CARIBE-EWS XVII

## OVERVIEW
CARIBE-EWS ACTION MONITOR OVERVIEW
2025-05-05 | COMPLETED | IN PROGRESS | DELAYED | FAILED | NOT STARTED | CANCELED | TOTAL
# | 22 | 31 | 1 | 3 | 7 | 0 | 64
% | 34.375 | 48.4375 | 1.5625 | 4.6875 | 10.9375 | 0 | 100