## OTGA-SG IV-V (IODE-28)
OTGA PROGRAMME COMPONENT: BUDGET BY OUTCOME, OUTPUT, ACTIVITY (2025-26)
| Outcome, output and key activity | 2026 - aproved IODE-28 | 2026 - aproved IODE-28 (updated) | Priority
[5 empty] | 2026 |  | Priority
Outcome 1 | Increased capacity and skills by ocean specialists to use standards and best practices tools towards achieving SDG 14. |  |  |  | Forseen expense | Cost
Output 1 | Learners empowered to apply the skills learned and influencing the implementation and the use of standards and best practices widely accepted
Activity 1 | Organize and host training courses relevant to the Regions | 5000 | 5000 | MEDIUM
Activity 2 | Provide travel grants to facilitate attendance at training courses | 35000 | 35000 | MEDIUM | Onsite training courses | 40000 | MEDIUM
Activity 3 | Provide technical support eLearning platform | 17000 | 17000 | HIGH | e-Learning Developer/All-in support contract | 17000 | HIGH
Activity 4 | Confirm certification of the Project Office as LSP (April) | 3500 | 2000 | HIGH | ISO audit | 2000 | HIGH
Output 2 | Production of new knowledge and training resources |  |  |  | Individual Consultant (subject expert) | 20000 | MEDIUM
Activity 1 | Design and develop new or existing course content to address the capacity needs of IOC Programmes | 20000 | 20000 | MEDIUM | Individual Consultant (e-Learning officer) | 40000 | HIGH
Activity 2 | Update existing OTGA content to ensure it meets current OTGA course management guidelines | 10000 | 10000 | HIGH | OTGA-SG | 20000 | LOW
Activity 3 | Upload training resources on the OTGA e-Learning Platform | 10000 | 10000 | HIGH | Communication material | 2500 | LOW
Activity 4 | Liaise with content providers on course design and presentation | 5000 | 10000 | HIGH | Secretariat travel | 8500 | MEDIUM
Output 3 | Promote a network of support and community building
Activity 1 | Update and publish regular CD communication through social media, newsletters and other communication, guidelines and best Practices documentation | 2500 | 2500 | LOW | TOTAL | 150000
Outcome 2 | Regional and Specialized Training Centres efficiently develop and manage the training programme
Output 1 | Increase capacity of Regional and Specialized Training Centres to develop and implement relevant training programmes
Activity 1 | Provide project governance framework through a steering group (November) | 25000 | 20000 | LOW
Activity 2 | Create and deliver online training for RTC/STC personnel | 5000 | 10000 | HIGH
Activity 3 | Update and publish OTGA Guidelines and Best Practices documentation | 5000
Output 2 | Increase awareness and understanding by MS on the benefits of supporting and promoting OTGA and the network of Training Centres
Activity 1 | Participate in conferences, meetings to promote OTGA | 7000 | 8500 | MEDIUM
| TOTAL | 150000 | 150000

## Workplan linked to RP
Objectives | Outcomes | Outputs (Programme Component) | Outputs (ToR) | Activities/tasks | Key Deliverable(s)/ Milestones | Dependencies/Adm arrangements | Priority/level of ambition (high, medium, low) | Estimated Start Date | Estimated Completion Date | Budget |  | Status | Risks
1. Develop, in collaboration with programmes across the IOC, a comprehensive learning management system to deliver customized training for equitable capacity related to ocean research, observations and services. | Outcome 1 - Increased capacity and skills by ocean specialists to use standards and best practices tools towards achieving SDG 14; Outcome 2 - Regional and Specialized Training Centres efficiently develop and manage the training programme | • Output 1 - Learners empowered to apply the skills learned and influencing the implementation and the use of standards and best practices widely accepted; • Output 2 - Production of new knowledge and training resources; • Output 3 - Promote a network of support and community building; • Output 4 - Increased capacity of Regional and Specialized Training Centres to develop and implement relevant training programmes; • Output 5 - Increase awareness and understanding by MS on the benefits of supporting and promoting OTGA and the network of Training Centres. | A customized Learning Management System and a shared e-Learning Platform | Host training materials and provide technical support through a shared eLearning platform | OTGA e-Learning platform active running, through all in support and mobile application | External developer - Service contract to be renewed | HIGH | cont. 1 January 2026 | cont. 31 December 2026 | 17000 | HIGH | ongoing, contract to be renewed | Operations will run under reduced support (low maintainance and no usual upgrades of OTGA e-Learning platform). Technical problems will need to be sorted out internally with the help of IODE IT/Arno and may take longer to be implemented or ultimetely unsolved, alternative aid solutions.
|  |  |  | Design and develop new or existing course content to address the capacity needs of IOC Programmes | 1 fully new training course developed and launched (mentioned in IOC Results framework) | Call for Individual Consultant | MEDIUM | 2026-08-01 | 2026-10-31 | 20000 | MEDIUM | not started | New training course expected not delivered or delayed. In-kind support of experts may be possible, but not having a consultant can add extra demand to OTGA Secretariat
2. Create and facilitate open and free access to new knowledge, learning resources, and training opportunities to support the needs and priorities of IOC Programmes, IOC Regional Subsidiary Bodies, IOC Member States, and beyond when needed. |  |  | Training courses and other knowledge-sharing activities planned, developed, and delivered, including the creation of learning resources and training materials, and facilitation of professional exchange | Core support on learning management frameworks, including update existing OTGA content to ensure it meets current OTGA course management guidelines, upload training resources on the OTGA e-Learning Platform, liaise with content providers on course design and presentation; Create and deliver online training for RTC/STC personnel | OTGA Secretariat activities completed, including launching and maintainance of the list of training courses requested by centres (~70%) | Call for Individual Consultant | HIGH | 2026-05-01 | 2026-11-30 | 40000 | HIGH | ongoing, new call needs to be issued or experts consulted | If the consultant is not replaced partially or fully, the capacity of OTGA Secretariat to deliver trainings and maintain its LMS will be highligh impacted.
|  |  | Enhanced and innovative opportunities for individual upskilling and institutional capacity development | Organize and host on-site training courses, including providing travel grants to facilitate attendance of training | 2 onsite training courses co-sponsored | Service contract - RTC/STCs | MEDIUM | tbc | tbc | 40000 | MEDIUM | pending (review of requests + adm) | No onsite trainings will be co-sponsored by OTGA, therefore, relying on other partners to be accomplished.
3. Coordinate, guide, and empower a global network of centres, partners, experts, and learners, through training and community building. |  |  | A global network of training centres, partners, experts, and learners: empowered with knowledge, increased capacity to develop, implement, and access training programmes, and active mechanisms for collaboration and sharing of technical expertise | Provide project governance framework through a steering group | OTGA SG VI meeting | Travel arrangements | LOW |  | Mid-November 2026 | 20000 | LOW | not started | OTGA SG VI will run online or hosted onsite through other sponsors
4. Promote the wide use of international standards and best practices on knowledge-sharing and training for ocean sciences. |  |  | Guidance on learning services procedures, standards, and best practices on knowledge-sharing and training updated, certified, and communicated. | Participate in conferences, meetings to promote OTGA | 2 missions of OTGA Secretariat staff (2 people) | Travel arrangements | MEDIUM | cont. 1 January 2026 | cont. 31 December 2026 | 8500 | MEDIUM | not started | OTGA Secretariat will not go on missions, impact on partnership settlements and networking is foreseen
|  |  |  | Audit LMS and confirm certification of the Project Office as LSP | ISO audit and certification confirmed | Service contract | HIGH | 2026-04-01 | 2026-04-01 | 2000 | HIGH | pending (confirmation + payment) | OTGA surveillance audit ISO 29993 will not be carried out, suspension of certification
|  |  |  | Update and publish regular CD communication through social media, newsletters and other communication, including guidelines and best practices documentation | Communication materials and documentation updated and printed | Service contract | LOW | cont. 1 January 2026 | cont. 31 December 2026 | 2500 | LOW | not started | Printed OTGA communication materials will not be updated or available
[9 empty] | TOTAL | 150000